## gantt
wp | activity | start_date | end_date
Scoping and planning | 1. Draft proposal | 2023-12-18 | 2024-01-12
Scoping and planning | 2. Background information | 2024-01-01 | 2024-01-12
Scoping and planning | 3. Project setup | 2024-01-08 | 2024-01-12
Literature | 1. Establish search strategy | 2024-01-15 | 2024-01-26
Literature | 2. Execute search | 2024-01-29 | 2024-02-02
Literature | 3. Review and synthesise | 2024-02-05 | 2024-02-16
Data collection | 1. Scraping published data | 2024-02-19 | 2024-02-23
Data collection | 2. Routine data extracts | 2024-02-19 | 2024-02-23
Data collection | 3. Request / process bespoke | 2024-02-19 | 2024-03-01
Analysis | 1. Wrangling and recoding | 2024-03-04 | 2024-03-15
Analysis | 2. Apply methods | 2024-03-18 | 2024-03-29
Analysis | 3. Validate | 2024-04-01 | 2024-04-05
Analysis | 4. Visualise outputs | 2024-04-01 | 2024-04-12
Reporting | 1. Draft report | 2024-03-04 | 2024-04-26
Reporting | 2. Share & revise | 2024-04-29 | 2024-05-17
Reporting | 3. Disseminate final report | 2024-05-20 | 2024-05-24

## spots
activity | spot_type | spot_date
3. Project setup | M | 2024-01-03
3. Review and synthesise | R | 2024-02-15
3. Request / process bespoke | M | 2024-02-28
4. Visualise outputs | M | 2024-04-11
3. Disseminate final report | R | 2024-05-20
3. Disseminate final report | P | 2024-05-24